## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | NENDARPAR PWSS | SM/18137 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for NENDARPAR water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000982/2023-2024 | 2614/NMD-II | 25/08/2023 | 24/09/2023 | SANJIB SAHA | 22.05 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | NENDARPAR PWSS | SM/18137 | New | PROVIDING FHTC AT CHHOTA KESHARIBARI PWSS |  |  | BILL/02050/2023-2024 | BP-1281-P2 | 28/03/2024 |  | M/S KARNATAKA CONSTRUCTION COMPANY | 0 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | NENDARPAR PWSS | SM/18137 | New | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | NENDARPAR PWSS | SM/18137 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | NENDARPAR PWSS | SM/18137 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NENDARPAR TW I. |  |  | BILL/00520/2024-2025 | BP-114/24-25 | 24/05/2024 |  | WBSEDCL | 4.65 | 0 | 0 | null
6 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | NENDARPAR PWSS | SM/18137 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NENDARPAR TW I. |  |  | BILL/00520/2024-2025 | BP-114/24-25 | 24/05/2024 |  | WBSEDCL | 4.65 | 0 | 0 | null
7 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | NENDARPAR PWSS | SM/18137 | New | Execution of different works related to NENDARPAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000504/2023-2024 | 300/CD | 09/02/2024 | 09/04/2024 | BIJOY ROY | 59.36 | 0 | 0 | 70
8 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | NENDARPAR PWSS | SM/18137 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NENDARPAR TW II. |  |  | BILL/00643/2024-2025 | BP-161/24-25 | 21/06/2024 |  | WBSEDCL | 3.89 | 0 | 0 | null
9 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | NENDARPAR PWSS | SM/18137 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NENDARPAR TW II. |  |  | BILL/00643/2024-2025 | BP-161/24-25 | 21/06/2024 |  | WBSEDCL | 3.89 | 0 | 0 | null
10 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | NENDARPAR PWSS | SM/18137 | New | Execution of different works related to NENDAPAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000092/2023-2024 | 627/CD | 12/07/2023 | 09/12/2023 | BIJOY ROY | 267.57 | 143.27 | 53.55 | 80
11 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | NENDARPAR PWSS | SM/18137 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20312.73 | 143.27 | 0.71