## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to Chandamari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000045/2023-2024 | 406/CD | 23/05/2023 | 01/01/2026 | MS DD ENTERPRISE | 111.16 | 89.05 | 80.11 | 95
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for CHANDAMARI Water Supply Scheme TW No.- I AND II under NMD-II, PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001068/2023-2024 | 2709/NMD-II | 19/09/2023 | 19/10/2023 | M/S ABHISEK ENGINEERING CONCERN | 21.83 | 6.94 | 31.78 | 100
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000115/2023-2024 | 640/CD | 12/07/2023 | 10/09/2023 | SENGUPTA ENTERPRISE | 17.17 | 17.16 | 99.96 | 100
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000325/2023-2024 | 1308/CD | 24/11/2023 | 23/01/2024 | RAJAT ROY | 4.39 | 4.39 | 100 | 1
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000523/2023-2024 | 321/cd | 09/02/2024 | 02/11/2025 | MS DD ENTERPRISE | 45.77 | 45.15 | 98.66 | 100
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN CHANDAMARI , GHARGHARIA ZONE-II , KURSHAMARI AREA) PHALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000591/2024-2025 | 2275/CD | 23/12/2024 | 15/02/2026 | TAPAN CHANDA | 86.58 | 0 | 0 | 30
7 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHANDAMARI TW II. |  |  | BILL/00638/2024-2025 | BP-155/24-25 | 20/06/2024 | 20/06/2024 | WBSEDCL | 2.88 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHNDAMARI TW III. |  |  | BILL/00639/2024-2025 | BP-156/24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL | 5.86 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | HIRING VEHICLE FOR TFG/JE |  |  | BILL/00562/2024-2025 | BP-214 | 31/07/2024 | 31/07/2024 | GOUTAM KUMAR DAS | 0.58 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASI and others) under JJM in the BLOCK: Mathabhanga-I, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000139/2025-2026 | 1348/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 34.38 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | Solarization of grid connected pumping installation at Different PWSS at Mathabhanga-I Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000167/2025-2026 | 1388/NMD-II | 26/06/2025 | 24/09/2025 | E AND C ENGINEERING & CONSULTANCY SERVICES PRIVATE LIMITED | 47.89 | 0 | 0 | 30
13 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | ADDITIONAL ELECTRIC QUOTATION FOR NSC AT CHANDAMARI TW II. |  |  | BILL/02169/2024-2025 | BP-467/24-25 | 21/01/2025 | 21/01/2025 | WBSEDCL | 0.39 | 0 | 0 | 0
Total | [13 empty] | 866.94 | 162.69 | 18.77