## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for CHANDAMARI Water Supply Scheme TW No.- I AND II under NMD-II, PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001068/2023-2024 | 2709/NMD-II | 19/09/2023 | 19/10/2023 | M/S ABHISEK ENGINEERING CONCERN | 21.83 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000115/2023-2024 | 640/CD | 12/07/2023 | 10/09/2023 | SENGUPTA ENTERPRISE | 17.17 | 17.16 | 99.96 | 100
3 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to Chandamari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000045/2023-2024 | 406/CD | 23/05/2023 | 20/10/2023 | MS DD ENTERPRISE | 111.16 | 36.31 | 32.67 | 65
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000325/2023-2024 | 1308/CD | 24/11/2023 | 23/01/2024 | RAJAT ROY | 4.39 | 0 | 0 | 1
5 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHANDAMARI TW II. |  |  | BILL/00638/2024-2025 | BP-155/24-25 | 20/06/2024 |  | WBSEDCL | 2.88 | 0 | 0 | null
6 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHANDAMARI TW II. |  |  | BILL/00638/2024-2025 | BP-155/24-25 | 20/06/2024 |  | WBSEDCL | 2.88 | 0 | 0 | null
7 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHANDAMARI PWSS | SM/18138 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHNDAMARI TW III. |  |  | BILL/00639/2024-2025 | BP-156/24-25 | 21/06/2024 |  | WBSEDCL | 5.86 | 0 | 0 | null
8 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHANDAMARI PWSS | SM/18138 | New | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000523/2023-2024 | 321/cd | 09/02/2024 | 09/05/2024 | MS DD ENTERPRISE | 45.77 | 0 | 0 | 60
Total | [13 empty] | 211.93 | 53.47 | 25.23