## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | FHTC AND OTHER ALLILED WORKS AT LAUCHAPRA PWSS |  |  | BILL/01088/2023-2024 | BP-700 | 19/10/2023 |  | NANDALAL SARKAR | 8 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for KURSHAMARI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000988/2023-2024 | 2618/NMD-II | 25/08/2023 | 24/09/2023 | SAIKAT SINHA | 22.05 | 8.67 | 39.31 | 30
3 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | Execution of different works related to AUG. of Kurshamari PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 11/1-5/NBC-1; Dt.: 05-04-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000290/2023-2024 | 11/CD | 05/04/2023 | 02/09/2023 | SUBHAS CHANDRA ROY | 301.82 | 100.7 | 33.37 | 75
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | Execution of different works related to KURSHAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000040/2024-2025 | 1148/CD | 14/06/2024 | 13/08/2024 | SUBHAS CHANDRA ROY | 45.55 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | FHTC AT KURSHAMARI PWSS |  |  | BILL/01141/2023-2024 | null | 14/11/2023 |  | SUBHAS CHANDRA ROY | 0 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KHURSAMARI TW NO II. |  |  | BILL/00279/2024-2025 | BP-77/24-25 | 15/05/2024 |  | WBSEDCL | 1.15 | 0 | 0 | null
7 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KURSHAMARI TW NO. II |  |  | BILL/00338/2024-2025 | null | 20/05/2024 |  | WBSEDCL | 7.45 | 0 | 0 | null
8 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KHURSAMARI TW I. |  |  | BILL/00637/2024-2025 | BP-218/24-25 | 15/07/2024 |  | WBSEDCL | 4.09 | 0 | 0 | null
9 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KHURSAMARI TW I. |  |  | BILL/00637/2024-2025 | BP-218/24-25 | 15/07/2024 |  | WBSEDCL | 4.09 | 0 | 0 | null
10 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KURSHAMARI TW II. |  |  | BILL/00644/2024-2025 | BP-219/24-25 | 15/07/2024 |  | WBSEDCL | 6.54 | 0 | 0 | null
11 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | Execution of different works related to KURSHAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000340/2023-2024 | 1397/CD | 05/12/2023 | 03/02/2024 | SUBHAS CHANDRA ROY | 50.91 | 0 | 0 | 90
Total | [13 empty] | 451.66 | 109.37 | 24.22