## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | FHTC AND OTHER ALLILED WORKS AT LAUCHAPRA PWSS |  |  | BILL/01088/2023-2024 | BP-700 | 19/10/2023 | 19/10/2023 | NANDALAL SARKAR | 8 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | Execution of different works related to KURSHAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000340/2023-2024 | 1397/CD | 05/12/2023 | 03/02/2024 | SUBHAS CHANDRA ROY | 50.91 | 26.76 | 52.57 | 90
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | Execution of different works related to KURSHAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000040/2024-2025 | 1148/CD | 14/06/2024 | 13/08/2024 | SUBHAS CHANDRA ROY | 45.55 | 39.21 | 86.08 | 60
4 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KHURSAMARI TW NO II. |  |  | BILL/00279/2024-2025 | BP-77/24-25 | 15/05/2024 | 15/05/2024 | WBSEDCL | 1.15 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KURSHAMARI TW II. |  |  | BILL/00644/2024-2025 | BP-219/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 6.54 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KHURSAMARI TW I. |  |  | BILL/00637/2024-2025 | BP-218/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | FHTC AT KURSHAMARI PWSS |  |  | BILL/01141/2023-2024 |  | 14/11/2023 | 14/11/2023 | SUBHAS CHANDRA ROY | 0 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | Execution of different works related to AUG. of Kurshamari PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 11/1-5/NBC-1; Dt.: 05-04-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000290/2023-2024 | 11/CD | 05/04/2023 | 24/04/2025 | SUBHAS CHANDRA ROY | 301.82 | 233.91 | 77.5 | 75
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | Ground water based KURSHAMARI PWSS | SM/18139 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN CHANDAMARI , GHARGHARIA ZONE-II , KURSHAMARI AREA) PHALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000591/2024-2025 | 2275/CD | 23/12/2024 | 20/09/2025 | TAPAN CHANDA | 86.58 | 0 | 0 | 30
10 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASI and others) under JJM in the BLOCK: Mathabhanga-I, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000139/2025-2026 | 1348/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 34.38 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | Ground water based KURSHAMARI PWSS | SM/18139 | New | Solarization of grid connected pumping installation at Different PWSS at Mathabhanga-I Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000167/2025-2026 | 1388/NMD-II | 26/06/2025 | 24/09/2025 | E AND C ENGINEERING & CONSULTANCY SERVICES PRIVATE LIMITED | 47.89 | 0 | 0 | 0
Total | [13 empty] | 1074.99 | 299.88 | 27.9