## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mekliganj | Coochbehar Division | ANDARAN KUCHLIBARI PWSS | SM/18140 | New | EXECUTION OF DIFFERENT WORKS RELATED TO Kuchlibari Zone-I, KUCHLIBARI ZONE-II AND ANDARAN KUCHLIBARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000527/2024-2025 | 2290/CD | 23/12/2024 | 21/02/2025 | M/S BADAL CH SAHA | 94.71 | 0 | 0 | 0
2 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | ANDARAN KUCHLIBARI PWSS | SM/18140 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ANDARAN KUCHLIBARI TW I. |  |  | BILL/02017/2024-2025 | BP-429/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 10.5 | 0 | 0 | 0
3 | COOCHBEHAR | Mekliganj | Coochbehar Division | ANDARAN KUCHLIBARI PWSS | SM/18140 | New | Execution of different works related to ANDARAN KUCHLIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000158/2023-2024 | 888/CD | 25/08/2023 | 17/02/2026 | M/S BADAL CH SAHA | 109.2 | 0 | 0 | 30
4 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | ANDARAN KUCHLIBARI PWSS | SM/18140 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for ANDRAN KUCHLIBARI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. |  |  | ORD/000985/2023-2024 | 2616/NMD-II | 25/08/2023 | 24/09/2023 | CHOWDHURY AND BASU ENTERPRISE | 22.05 | 0 | 0 | 0
5 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | ANDARAN KUCHLIBARI PWSS | SM/18140 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
Total | [13 empty] | 724.53 | 0 | 0