## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Execution of IEC activities related to judicious & safe use of drinking water, water conservation, water quality issues under JAL JEEVAN MISSION support activities at Cooch Behar District (Part-B) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000234/2023-2024 | 936/CD | 04/09/2023 | 04/08/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 148.47 | 80.21 | 54.02 | 28
2 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Central team visit at different GP programme & Villages and PWSS in 12 nos of Block under Coochbehar Division PHE Dte.(19/02/2024 to 21/02/2024) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000807/2023-2024 | 340/CD | 19/02/2024 | 26/02/2024 | MATARA CONSTRUCTION CO. | 0.98 | 0.98 | 100 | 100
3 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Central team visit at different GP programme & Villages and PWSS in 12 nos of Block under Coochbehar Division PHE Dte.(22/02/2024 to 24/02/2024) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000808/2023-2024 | 345/CD | 20/02/2024 | 27/02/2024 | MATARA CONSTRUCTION CO. | 0.96 | 0.96 | 100 | 100
4 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | FUEL BILL |  |  | BILL/00588/2024-2025 | BP-222 | 01/08/2024 | 01/08/2024 | SUCHITRO FUEL STATION | 0.6 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Central team visit different GP programme & Villages and PWSS in 12 nos of Block under Coochbehar Division PHE Dte.(28/07/2024-31/07/2024) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000482/2024-2025 | 1348/CD | 25/07/2024 | 30/07/2024 | BIJOY ROY | 0.99 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Execution of IEC activities related to judicious & safe use of drinking water, water conservation, water quality issues under JAL JEEVAN MISSION support activities at Cooch Behar District (Block-Dinhata-I) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000115/2025-2026 | 983/CD | 25/06/2025 | 06/07/2025 | RASID ALAM | 0.95 | 0 | 0 | 100
7 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Execution of IEC activities related to judicious & safe use of drinking water, water conservation, water quality issues under JAL JEEVAN MISSION support activities at Cooch Behar District (Block-Cooch Behar-II) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000118/2025-2026 | 1137/CD | 01/07/2025 | 09/07/2025 | RASID ALAM | 0.69 | 0 | 0 | 100
Total | [13 empty] | 153.64 | 82.15 | 53.47