## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities | SM/18162 | Support-IEC | Execution of IEC activities related to judicious & safe use of drinking water, water conservation, water quality issues under JAL JEEVAN MISSION support activities at Cooch Behar District (Part-B) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000234/2023-2024 | 936/CD | 04/09/2023 | 04/08/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 148.47 | 59.33 | 39.96 | 28
Total | [13 empty] | 148.47 | 59.33 | 39.96