## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN SAMILABAS PWSS | SM/18183 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DAKSHIN SAMILABAS water supply scheme, TW no I under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001146/2023-2024 | 2867/NMD-II | 17/10/2023 | 29/04/2025 | M/S J.K ENGINEERING CO. | 11.02 | 7.76 | 70.42 | 20
2 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN SAMILABAS PWSS | SM/18183 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DAKSHIN SAMILABAS PWSS TW I |  |  | BILL/02727/2023-2024 | BP-2023-24-602 | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.98 | 0 | 0 | 0
3 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN SAMILABAS PWSS | SM/18183 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000280/2025-2026 | 787/CD | 23/05/2025 | 21/08/2025 | CONSTRUCTION DEVELOPMENT PROJECT | 79.37 | 0 | 0 | 0
4 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN SAMILABAS PWSS | SM/18183 | New | Execution of different works related to DAKSHIN SAMILABAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000135/2023-2024 | 803/CD | 08/08/2023 | 25/11/2025 | MS N S CONSTRUCTION | 159.73 | 110.51 | 69.18 | 30
5 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN SAMILABAS PWSS | SM/18183 | New | ELECTRIC QUOTATION BILL FOR NSC AT DAKSHIN SAMILABAS PH-II. |  |  | BILL/01715/2025-2026 |  | 21/08/2025 | 21/08/2025 | WBSEDCL | 6.78 | 0 | 0 | 0
6 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN SAMILABAS PWSS | SM/18183 | New | EXECUTION OF DIFFERENT WORKS RELATED TO HEMKUMARI ZONE-II HEMKUMARI ZONE-III & DAKSHIN SAMILABAS PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000532/2024-2025 | 2216/CD | 23/12/2024 | 15/04/2026 | M/S N S CONSTRUCTION | 39.17 | 0 | 0 | 50
Total | [13 empty] | 300.05 | 118.27 | 39.42