## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | NAKARJAN AND ITS ADJOINING MOUZAS PWSS | SM/18239 | New | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 91/CD | 11/01/2024 | 11/01/2024 | Resource Division | 15.52 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | NAKARJAN AND ITS ADJOINING MOUZAS PWSS | SM/18239 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NAKARJAN TW NO. I. |  |  | BILL/02611/2023-2024 | BP-2023-24-574 | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.9 | 0 | 0 | 0
3 | COOCHBEHAR | Sitai | Northern Mechanical Division II | NAKARJAN AND ITS ADJOINING MOUZAS PWSS | SM/18239 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NAKARJAN TW NO. II. |  |  | BILL/02805/2023-2024 | BP-2023-24-645 | 29/02/2024 | 29/02/2024 | WBSEDCL | 11.19 | 0 | 0 | 0
4 | COOCHBEHAR | Sitai | Coochbehar Division | NAKARJAN AND ITS ADJOINING MOUZAS PWSS | SM/18239 | New | Execution of different works related to NAKARANJAN PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000097/2023-2024 | 632/CD | 12/07/2023 | 05/12/2025 | JAL PRAVAHIKA PVT. LTD. | 609.32 | 397.09 | 65.17 | 80
5 | COOCHBEHAR | Sitai | Coochbehar Division | NAKARJAN AND ITS ADJOINING MOUZAS PWSS | SM/18239 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR | Sitai | Coochbehar Division | NAKARJAN AND ITS ADJOINING MOUZAS PWSS | SM/18239 | New | EXECUTION OF DIFFERENT WORKS RELATED TO SITAI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000611/2024-2025 | 2312/CD | 23/12/2024 | 20/08/2025 | RAHAMAN ENTERPRISE | 27.34 | 0 | 0 | 90
Total | [13 empty] | 20457.57 | 397.09 | 1.94