## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 249/CD | 27/04/2023 | 27/04/2023 | Resource Division | 32.04 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | QUOTATION FOR NSC AT CHOTO BOALMARI TW NO ii |  |  | BILL/00997/2023-2024 |  | 04/07/2023 | 04/07/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHHOTO BOALMARI PWSS TW NO -I |  |  | BILL/01441/2023-2024 | BP-2023-24-277 | 18/08/2023 | 18/08/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | QUOTATION FOR NSC AT CHOTO BOALMARI TW NO i |  |  | BILL/00998/2023-2024 |  | 27/06/2023 | 27/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHHOTO BOALMARI PWSS TW NO -II |  |  | BILL/01442/2023-2024 | BP-2023-24-280 | 18/08/2023 | 18/08/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Chhoto Boalmari Water Supply Scheme TW No.- I,II, III and IV under NMD-II,PHE.Dte,APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000784/2023-2024 | 2284/NMD-II | 31/07/2023 | 30/08/2023 | DAS ENTERPRISE | 40.62 | 14.01 | 34.49 | 50
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part I | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000587/2023-2024 | 624/CD | 11/03/2024 | 10/05/2024 | RHYNO INFRASTRUCTURE | 99.34 | 18.51 | 18.64 | 100
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari, CHHOTO BOALMARI Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000498/2024-2025 | 1379/CD | 31/07/2024 | 31/10/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-II, CHHOTO BOALMARI Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000496/2024-2025 | 1116/CD | 13/06/2024 | 13/09/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I, CHHOTO BOALMARI Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000495/2024-2025 | 1110/CD | 10/06/2024 | 10/09/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj, CHHOTO BOALMARI Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000497/2024-2025 | 1378/CD | 31/07/2024 | 31/10/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
12 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 20/CD | 05/01/2024 | 05/01/2024 | Resource Division | 18.52 | 0 | 0 | 0
13 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Execution of different works related to CHHOTO BOALMARI (ZONE-ii) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000094/2023-2024 | 629/CD | 12/07/2023 | 06/08/2025 | S & P ENTERPRISE | 376.33 | 143.47 | 38.12 | 30
14 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
15 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000276/2025-2026 | 738/CD | 17/05/2025 | 15/08/2025 | SUBHAS CHANDRA ROY | 47.78 | 0 | 0 | 0
16 | COOCHBEHAR | Dinhata-I | Coochbehar Division | CHHOTO BOALMARI PIPED WATER SUPPLY SCHEME. | SM/18240 | New | Execution of different works related to CHHOTO BOALMARI z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000091/2023-2024 | 626/CD | 12/07/2023 | 28/12/2025 | S & P ENTERPRISE | 437.76 | 344.47 | 78.69 | 25
Total | [13 empty] | 20850.08 | 524.4 | 2.52