## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 246/CD | 27/04/2023 | 27/04/2023 | Resource Division | 53.87 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000166/2023-2024 | 943/CD | 04/09/2023 | 03/12/2023 | MATARA CONSTRUCTION CO. | 4.98 | 4.98 | 99.98 | 100
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Name of Work: Execution of different works related to PESTARJHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000274/2023-2024 | 1031/CD | 22/09/2023 | 21/11/2023 | SWAPAN KR.SARKAR | 29.76 | 29.75 | 99.98 | 100
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Execution of different works related to PESTARJHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000420/2023-2024 | 1386/CD | 05/12/2023 | 03/02/2024 | SANKAR BANIK | 2.7 | 2.7 | 100 | 100
5 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Execution of different works related (within area of DHALUABARI) to PESTARJHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000066/2024-2025 | 1323/CD | 19/07/2024 | 17/10/2024 | SWAPAN KR.SARKAR | 34.6 | 34.58 | 99.93 | 95
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 27/CD | 05/01/2024 | 05/01/2024 | Resource Division | 21.55 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | PESTARJHAR PWSS | SM/18248 | New | New service connection at PESTARJHAR PWSS Z-II, PH-I |  |  | BILL/02024/2024-2025 | BP-446/24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL | 5.45 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | PESTARJHAR PWSS | SM/18248 | New | NEW SERVICE CONNECTION AT PESTARJHAR ZONE-II, PH-II |  |  | BILL/02023/2024-2025 | BP-450/24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL | 6.04 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | EXECUTION OF DIFFERENT WORK AT GHOKSHSADANGA PWSS |  |  | BILL/01992/2023-2024 | BP-1348-P2 | 30/03/2024 | 30/03/2024 | Z STAR COMMOTRADE PVT LTD | 0 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | PESTARJHAR PWSS | SM/18248 | New | NEW SERVICE CONNECTION CHARGES FOR PESTARJHAR, ZONE-I, PH-II |  |  | BILL/00766/2024-2025 | BP-222/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 1.06 | 0 | 0 | 0
11 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | HIRING VEHICLE FOR AE/HQ |  |  | BILL/00543/2024-2025 | BP-211 | 31/07/2024 | 31/07/2024 | BHAGWATI BHUJEL | 0.35 | 0 | 0 | 0
12 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | EXECUTIN OF DIFFERENT WORK AT LOTAPOTA PWSS |  |  | BILL/02014/2023-2024 | BP-1391-P1 | 31/03/2024 | 31/03/2024 | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 0 | 0 | 0 | 0
13 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | PESTARJHAR PWSS | SM/18248 | New | New service connection charges for Pestarjhar, Zone - I, PH - I, Under NMD-II, PHE,Dte. |  |  | BILL/00889/2024-2025 | BP-274/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 7.36 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Execution of different works related to PESTARJHAR Zone - I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000095/2023-2024 | 630/CD | 12/07/2023 | 07/01/2026 | SWAPAN KR.SARKAR | 278.76 | 199.42 | 71.54 | 34
15 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Execution of different works related to PESTARJHAR Zone - II & III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000096/2023-2024 | 631/CD | 12/07/2023 | 07/08/2025 | M/S. DUTTA AND CO | 494.72 | 306.8 | 62.01 | 55
16 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
17 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000526/2024-2025 | 2289/CD | 23/12/2024 | 21/02/2026 | HIRAK CONSTRUCTION | 34.93 | 0 | 0 | 90
18 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
19 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | PESTARJHAR PWSS | SM/18248 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Pestarjhar Water Supply Scheme TW No.- I , II of Zone-I and TW No- I and II of Zone-II under Jal Jeevan Mission NMDII, PHE.Dte,Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000273/2024-2025 | 2269/NMD-II | 10/09/2024 | 17/06/2025 | QUAZI NOZRUL ISLAM | 44.16 | 0 | 0 | 90
20 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000035/2025-2026 | 720/CD | 17/05/2025 | 15/08/2025 | BIJOY ROY | 27.61 | 0 | 0 | 95
21 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | PESTARJHAR PWSS | SM/18248 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000124/2025-2026 | 760/CD | 17/05/2025 | 15/08/2025 | M/S. DUTTA AND CO | 69.29 | 0 | 0 | 50
22 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | PESTARJHAR PWSS | SM/18248 | New | New service connection charges for Pestarjhar, Zone-I, PH- II, under NMD-II, Phe,Dte. |  |  | BILL/02976/2025-2026 |  | 13/01/2026 | 13/01/2026 | WBSEDCL | 1.06 | 0 | 0 | 0
Total | [13 empty] | 20975.06 | 578.22 | 2.76