## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Execution of different works related to DUDHERKUTHI DEWANBAS PWSS under JAL JEEVAN MISSION |  |  | ORD/000075/2024-2025 | 1183/CD | 19/06/2024 | 18/08/2024 | SUDIP BASAK | 9.9 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Execution of different works related (within DUD KUTHIDEWANBAS ) to AUG. of DEWANHAT PWSS under JAL JEEVAN MISSION |  |  | ORD/000596/2023-2024 | 637/CD | 11/03/2024 | 10/05/2024 | M/S A. B. ENTERPRISE | 25.21 | 0 | 0 | 85
3 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Execution of different works related to DUDHER KUTHIDEWANBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000049/2024-2025 | 1158/CD | 14/06/2024 | 12/09/2024 | M/S A. B. ENTERPRISE | 95.63 | 0 | 0 | 30
4 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within DUDDER KUTHIDEWANBAS area) PATCHHARA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000590/2024-2025 | 2274CD | 23/12/2024 | 21/02/2025 | TORSHA CONSTRUCTION | 69.79 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II, DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000330/2024-2025 | 848/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
6 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I, DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000329/2024-2025 | 847/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
7 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I, DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000327/2024-2025 | 845/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
8 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II, DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000328/2024-2025 | 846/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
9 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II, DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000332/2024-2025 | 850/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
10 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I, DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000331/2024-2025 | 849/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
11 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 23/CD | 05/01/2024 | 05/01/2024 | Resource Division | 21.63 | 0 | 0 | 0
12 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Northern Mechanical Division II | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | NEW SERVICE CONNECTION CHARGES AT DUDHERKUTHI DEWANBAS PWSS , ZONE-II, PH-II |  |  | BILL/02873/2023-2024 | BP-2023-24-657 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
13 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | HIRING VEHICLE FOR EE/CD |  |  | BILL/00563/2024-2025 | BP-210 | 31/07/2024 | 31/07/2024 | SWAPAN KR.SARKAR | 1.22 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Northern Mechanical Division II | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | NEW SERVICE CONNECTION CHARGES AT DUDHERKUTHI NDEWANBAS PWSS, ZONE-II, PH-I |  |  | BILL/02880/2023-2024 | BP-2023-24-658 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
15 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Execution of different works related to DUDHER KUTHIDEWANBAS Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000089/2023-2024 | 624/CD | 12/07/2023 | 09/12/2023 | S & P ENTERPRISE | 339.16 | 0 | 0 | 32
16 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Execution of different works related to DUDHER KUTHIDEWANBAS Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000090/2023-2024 | 625/CD | 12/07/2023 | 03/01/2026 | S & P ENTERPRISE | 464.91 | 0 | 0 | 40
17 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Coochbehar Division | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Execution of different works related to DEWANHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000333/2023-2024 | 1302/CD | 24/11/2023 | 25/05/2025 | DAS ENTERPRISE | 83.87 | 0 | 0 | 70
18 | COOCHBEHAR | Cooch Behar-I,Cooch Behar-II | Northern Mechanical Division II | DUDDER KUTHIDEWANBAS PIPED WATER SUPPLY SCHEME. | SM/18251 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DUDHERKUTHI DEWANBAS water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000859/2023-2024 | 2441/NMD-II | 11/08/2023 | 10/09/2023 | CHOWDHURY AND BASU ENTERPRISE | 42.27 | 0 | 0 | 100
Total | [13 empty] | 1170.18 | 0 | 0