## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | Execution of different works related to CHENGERKUTHI KHALISAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000101/2023-2024 | 715/CD | 25/07/2023 | 10/01/2026 | SHREE RANI SATI ENTERPRISE | 689.38 | 557.31 | 80.84 | 45
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Chengerkuthi Khalisamari Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001142/2023-2024 | 2885/NMD-II | 17/10/2023 | 19/05/2025 | CHOWDHURY AND BASU ENTERPRISE | 21.39 | 0 | 0 | 60
3 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
4 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | EXECUTION OF DIFFERENT WORKS RELATED TO CHENGERKUTHI KHALISAMARI & BARA GODAIKHORA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000521/2024-2025 | 2291/CD | 23/12/2024 | 24/08/2025 | UDAY CHAKI | 31.59 | 7.89 | 24.98 | 50
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000750/2024-2025 | 2272/CD | 23/12/2024 | 21/02/2025 | NORTH BENGAL CONSTRUCTION CO | 9.09 | 0 | 0 | 50
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 94/CD | 11/01/2024 | 11/01/2024 | Resource Division | 16.21 | 0 | 0 | 0
7 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHENGERKUTHI KHALISAMARI TW NO. I |  |  | BILL/00295/2024-2025 | BP-273/24-25 | 14/08/2024 | 14/08/2024 | WBSEDCL | 7.5 | 0 | 0 | 0
8 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | CHENGERKUTHI KHALISAMARI PWSS | SM/18284 | New | ELECTRIC QUOTATION BILL FOR NSC AT CHENGERKUTHI KHALISAMARI TW II. |  |  | BILL/00901/2025-2026 |  | 13/06/2025 | 13/06/2025 | WBSEDCL | 3.48 | 0 | 0 | 0
Total | [13 empty] | 20567.93 | 565.2 | 2.75