## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Execution of different works related to GURIAHATI (NM) (ZONE-I & II) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000102/2023-2024 | 716/CD | 25/07/2023 | 22/12/2023 | CONSTRUCTION AND CONSTRUCTION CO | 545.48 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 115/CD | 26/04/2023 | 26/04/2023 | Resource Division | 9.74 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Execution of different works related to GURIAHATI(NM) (ZONE- III) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000111/2023-2024 | 664/CD | 14/07/2023 | 11/12/2023 | MS TM CONSTRUCTION | 300.61 | 230.44 | 76.66 | 40
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Execution of different works related to GURIAHATI PWSS under JAL JEEVAN MISSION |  |  | ORD/000548/2023-2024 | 605/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 73.27 | 48.9 | 66.75 | 66
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Execution of different works related to CHHAT GURIAHATI PWSS under JAL JEEVAN MISSION Z3 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000027/2024-2025 | 1135/CD | 14/06/2024 | 13/08/2024 | SUBHAS CHANDRA ROY | 21.34 | 19.47 | 91.2 | 90
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | NEW SERVICE CONNECTION CHARGES AT GURIHATI (AUG) PWSS PH-IV |  |  | BILL/02878/2023-2024 | BP-2023-24-656 | 04/03/2024 | 04/03/2024 | WBSEDCL | 9.94 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | NEW SERVICE CONNECTION CHARGES AT GURIAHATI (AUG) PH-V |  |  | BILL/02889/2023-2024 | BP-2023-24-665 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.9 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | NEW SERVICE CONNECTION AT GURIAHATI (AUG) PWSS, PH-III |  |  | BILL/02886/2023-2024 | BP-2023-24-655 | 04/03/2024 | 04/03/2024 | WBSEDCL | 6.84 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Sajal Gram related to judicious & safe use drinking water under Jal Jeevan Mission (JJM) Support Activities at Cooch Behar District | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000434/2023-2024 | 52/CD | 10/01/2024 | 10/03/2025 | LIMRA SOCIAL WELFARE SOCIETY | 33.12 | 10.41 | 31.43 | 75
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Execution of different works related to AUG of GURIAHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000518/2023-2024 | 316/CD | 09/02/2024 | 08/04/2025 | SUBHAS CHANDRA ROY | 38.79 | 38.75 | 99.91 | 100
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | Execution of different works related to CHHAT GURIAHATI PWSS under JAL JEEVAN MISSION PART | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000046/2024-2025 | 1154/CD | 14/06/2024 | 10/04/2025 | SUBHAS CHANDRA ROY | 35.1 | 8.17 | 23.28 | 80
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Guriahati Pwss | SM/18297 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000073/2025-2026 | 788/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 75.53 | 0 | 0 | 0
Total | [13 empty] | 20944.94 | 356.14 | 1.7