## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 170/CD | 27/04/2023 |  | Resource Division | 31.38 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Preparation of DPR for Augmentation of Bara Atiabari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000302/2021-2022 | 1017/CD/W | 10/01/2022 | 30/01/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 3.6 | 3.6 | 100 | 100
3 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | New service connection at Bara atiabari PWSS, P/H-III |  |  | BILL/02211/2023-2024 | BP-2023-24-491 | 21/12/2023 |  | WBSEDCL | 4.41 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | New service connection at Bara atiabari PWSS, P/H-III |  |  | BILL/02211/2023-2024 | BP-2023-24-491 | 21/12/2023 |  | WBSEDCL | 4.41 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of Bara Atiabari Pratham Khanda water supply scheme, TW no I of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000863/2023-2024 | 2444/NMD-II | 11/08/2023 | 10/09/2023 | GEETA CONSTRUCTION | 27.85 | 0 | 0 | 40
6 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to B.ATIABARI P.KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000507/2023-2024 | 304/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 88.79 | 20.16 | 22.7 | 45
7 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to BARA ATIABARI P KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000061/2024-2025 | 1302/CD | 06/06/2024 | 04/09/2024 | MS SSB CONSTRUCTION CO | 86.73 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to BARA ATIABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000110/2023-2024 | 663/CD | 14/07/2023 | 11/12/2023 | MS SSB CONSTRUCTION CO | 652.47 | 354.38 | 54.31 | 60
Total | [13 empty] | 899.64 | 378.14 | 42.03