## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Preparation of DPR for Augmentation of Bara Atiabari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000302/2021-2022 | 1017/CD/W | 10/01/2022 | 30/01/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 3.6 | 3.6 | 100 | 100
2 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 170/CD | 27/04/2023 | 27/04/2023 | Resource Division | 31.38 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to B.ATIABARI P.KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000507/2023-2024 | 304/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 88.79 | 83.14 | 93.64 | 45
4 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to BARA ATIABARI P KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000061/2024-2025 | 1302/CD | 06/06/2024 | 04/09/2024 | MS SSB CONSTRUCTION CO | 86.73 | 85.59 | 98.68 | 30
5 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | New service connection at Bara atiabari PWSS, P/H-III |  |  | BILL/02211/2023-2024 | BP-2023-24-491 | 21/12/2023 | 21/12/2023 | WBSEDCL | 4.41 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to BARA ATIABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000110/2023-2024 | 663/CD | 14/07/2023 | 05/03/2025 | MS SSB CONSTRUCTION CO | 652.47 | 535.59 | 82.09 | 60
7 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of Bara Atiabari Pratham Khanda water supply scheme, TW no I of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000863/2023-2024 | 2444/NMD-II | 11/08/2023 | 24/03/2027 | GEETA CONSTRUCTION | 27.85 | 22.13 | 79.45 | 75
8 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000031/2025-2026 | 597/CD | 28/04/2025 | 23/01/2026 | SHRI ANNAPURNA DISTRIBUTORS | 67.29 | 0 | 0 | 30
9 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000054/2025-2026 | 602/CD | 28/04/2025 | 27/07/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO BARA ATIABARI PRATHAM KHANDA & PANISALA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000562/2024-2025 | 2247/CD | 23/12/2024 | 20/06/2025 | ABHIJIT KUMAR DAS | 30.94 | 0 | 0 | 30
11 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000083/2025-2026 | 725/CD | 17/05/2025 | 15/08/2025 | MS HOSSEN ELECTRICALS | 31.08 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000271/2025-2026 | 743/CD | 17/05/2025 | 15/08/2025 | M/S BADAL CH SAHA | 96.84 | 0 | 0 | 0
Total | [13 empty] | 1218.2 | 730.05 | 59.93