## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 165/CD | 27/04/2023 | 27/04/2023 | Resource Division | 14.02 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I, SHUKARUR KUTHI Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000487/2024-2025 | 1042/CD | 13/05/2024 | 13/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
3 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I, SHUKARUR KUTHI Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000485/2024-2025 | 997/CD | 29/04/2024 | 29/07/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
4 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II, SHUKARUR KUTHI Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000489/2024-2025 | 1043/CD | 14/05/2024 | 14/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II, SHUKARUR KUTHI Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000486/2024-2025 | 1041/CD | 09/05/2024 | 09/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 30/CD | 05/01/2024 | 05/01/2024 | Resource Division | 28.21 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | SHUKARUR KUTHI PWSS | SM/18327 | New | QUOTATION FOR NSC AT SUKARKUTHI TW NO I |  |  | BILL/02455/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 11.59 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | SHUKARUR KUTHI PWSS | SM/18327 | New | New service connection at Sukarurkuthi PWSS, P/H-II. |  |  | BILL/02322/2023-2024 | BP-2023-24-544 | 17/01/2024 | 17/01/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | SHUKARUR KUTHI PWSS | SM/18327 | New | New service connection at Sukarurkuthi PWSS, P/H-I. |  |  | BILL/02321/2023-2024 | BP-2023-24-545 | 17/01/2024 | 17/01/2024 | WBSEDCL | 11.59 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | SHUKARUR KUTHI PWSS | SM/18327 | New | QUOTATION FOR NSC AT SUKARKUTHI TW NO II |  |  | BILL/02454/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
11 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Execution of different works related to SHUKARUR KUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000103/2023-2024 | 717/CD | 25/07/2023 | 29/03/2025 | M/S JAYANTA KUMAR GOPE | 681.4 | 464.59 | 68.18 | 84
12 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 838.5 | 4.24 | 20
13 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
14 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000079/2025-2026 | 651/CD | 05/05/2025 | 03/08/2025 | GOUTAM KUMAR DAS | 91.22 | 0 | 0 | 0
15 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | SHUKARUR KUTHI PWSS | SM/18327 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Shukarur Kuthi water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001011/2023-2024 | 2593/NMD-II | 24/08/2023 | 02/06/2025 | M/S BHOWMIK & CO. | 21.84 | 0 | 0 | 80
16 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj, SHUKARUR KUTHI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000649/2024-2025 | 1862/CD | 28/10/2024 | 28/03/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
17 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari, SHUKARUR KUTHI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000650/2024-2025 | 1863/CD | 28/10/2024 | 28/03/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
18 | COOCHBEHAR | Dinhata-II | Coochbehar Division | SHUKARUR KUTHI PWSS | SM/18327 | New | HORDING/ SIGN BOARD FOR IEC CAMPAINING AT GP OFFICE / BLOCK OFFICE & DIFFERENT HEALTH CENTERS UNDER COOCH BEHAR DIVISION , PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000704/2024-2025 | 2326/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 48.03 | 0 | 0 | 100
Total | [13 empty] | 20780.07 | 1307.03 | 6.29