## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Execution of different works related to PATCHHARA ZONE 1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000107/2023-2024 | 660/CD | 14/07/2023 | 15/08/2025 | GHOSH AND SAHA CONSTRUCTION | 498.71 | 446.72 | 89.58 | 60
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PATCHHARA PWSS | SM/18368 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PATCHHARA water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000861/2023-2024 | 2442/NMD-II | 11/08/2023 | 01/04/2025 | SARKAR ELECTRIC | 42.39 | 4.09 | 9.65 | 70
3 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Execution of different works related to PATCHHARA Z I PWSS under JAL JEEVAN MISSION PART A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000483/2023-2024 | 285/CD | 09/02/2024 | 09/04/2024 | GHOSH AND SAHA CONSTRUCTION | 83.56 | 52.59 | 62.94 | 30
4 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within DUDDER KUTHIDEWANBAS area) PATCHHARA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000590/2024-2025 | 2274CD | 23/12/2024 | 21/02/2025 | TORSHA CONSTRUCTION | 69.79 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under PATCHHARA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-E) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000503/2024-2025 | 1048/CD | 14/05/2024 | 21/12/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
6 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under PATCHHARA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-F) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000504/2024-2025 | 1298(1)/CD | 11/07/2024 | 07/01/2025 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 19/CD | 05/01/2024 | 05/01/2024 | Resource Division | 24.18 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PATCHHARA PWSS | SM/18368 | New | NEW SERVICE CONNECTION AT PATCHARA PWSS, ZONE-II, PH-I |  |  | BILL/01024/2024-2025 | BP-302/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 19.19 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PATCHHARA PWSS | SM/18368 | New | NEW SERVICE CONNECTION AT PATCHARA PWSS , ZONE-II, PH-II |  |  | BILL/00841/2024-2025 | BP-254/24-25 | 06/08/2024 | 06/08/2024 | WBSEDCL | 8.59 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Execution of different works related to PATCHHARA ZONE 2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000147/2023-2024 | 859/CD | 22/08/2023 | 29/03/2026 | M/S TORSHA CONSTRUCTION | 354.17 | 201.92 | 57.01 | 33
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PATCHHARA PWSS | SM/18368 | New | Execution of different works related to PATCHHARA Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000605/2023-2024 | 651/CD | 11/03/2024 | 12/01/2025 | GHOSH AND SAHA CONSTRUCTION | 94.24 | 45.11 | 47.87 | 30
Total | [13 empty] | 20986.05 | 752.37 | 3.59