## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | Execution of different works related to DUDHERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000114/2023-2024 | 667/CD | 14/07/2023 | 05/03/2025 | MS SSB CONSTRUCTION CO | 764.99 | 708.21 | 92.58 | 39
2 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | Execution of different works related to DUDHERKUTHI Z1 PWSS under JAL JEEVAN MISSION |  |  | ORD/000552/2023-2024 | 656/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 88.15 | 50.43 | 57.21 | 57
3 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | Execution of different works related to DUDHERKUTHI Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000549/2023-2024 | 607/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 76.83 | 41.18 | 53.6 | 50
4 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 72/CD | 11/01/2024 | 11/01/2024 | Resource Division | 16.42 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | NEW SERVICE CONNECTION AT DUDHERKUTHI PWSS ZONE-II, PH-I |  |  | BILL/02888/2023-2024 | BP-2023-24-653 | 04/03/2024 | 04/03/2024 | WBSEDCL | 7.68 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | NEW SERVICE CONNECTION CHARGES AT DUDHERKATHI PESS, ZONE-II, PH-II |  |  | BILL/02884/2023-2024 | BP-2023-24-654 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.67 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | NEW SERVICE CONNECTION AT DUDHERKUTHI PWSS ZONE-I, PH-II |  |  | BILL/02085/2023-2024 |  | 19/02/2024 | 19/02/2024 | WBSEDCL | 14.82 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DUDHERKUTHI water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000865/2023-2024 | 2445/NMD-II | 11/08/2023 | 03/08/2025 | QUAZI NOZRUL ISLAM | 42.05 | 0 | 0 | 60
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | DUDDER KUTHI PIPED WATER SUPPLY SCHEME. | SM/18369 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000073/2025-2026 | 788/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 75.53 | 0 | 0 | 0
Total | [13 empty] | 1139.68 | 799.83 | 70.18