## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | New service connection for SHALBARI PWSS, PH-I |  |  | BILL/02064/2023-2024 | BP-2023-24-429 | 05/12/2023 | 05/12/2023 | WBSEDCL | 13.52 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | NEW SERVICE CONNECTION AT SHALBARI PWSS, ZONE-II, PH-II |  |  | BILL/02887/2023-2024 | BP-2023-24-651 | 04/03/2024 | 04/03/2024 | WBSEDCL | 8.4 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | NEW SERVICE CONNECTION CHARGES AT SHALBARI PWSS, Z-I, PH-II |  |  | BILL/02881/2023-2024 | BP-2023-24-652 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.44 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | Additional quotation for electrical infrastructure development work at Shalbari PWSS Z-I, PH-II |  |  | BILL/00765/2024-2025 | BP-225/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 3.15 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | Execution of different works related to SALBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000171/2023-2024 | 948/CD | 04/09/2023 | 20/02/2026 | AASHIRBAD ENTERPRISE | 99.3 | 73.98 | 74.5 | 50
6 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 299.94 | 1.52 | 20
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TUPAMARI DEWANBAS SHALBARI & PASCHIM MOYAMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000549/2024-2025 | 2234/CD | 23/12/2024 | 22/04/2025 | MATARA CONSTRUCTION CO. | 51.18 | 0 | 0 | 30
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | Execution of different works related to SHALBARI Z-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000044/2024-2025 | 1152/CD | 14/06/2024 | 06/02/2026 | M/S B PAUL AND COMPANY | 27.88 | 0 | 0 | 30
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | Execution of different works related to SHALBARI ZONE 2 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1344/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000625/2022-2023 | 1962/CD | 24/03/2023 | 11/02/2026 | M/S B PAUL AND COMPANY | 422.82 | 294.04 | 69.54 | 78
10 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | SHALBARI PIPED WATER SUPPLY SCHEME | SM/18370 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for SHALBARI water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000805/2023-2024 | 2383/NMD-II | 09/08/2023 | 08/08/2025 | B.B CONCERNED | 42.04 | 36.94 | 87.86 | 100
Total | [13 empty] | 20463.02 | 704.9 | 3.44