## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Execution of different works related to CHANDAMARI AREA PHALIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000572/2023-2024 | 614/CD | 11/03/2024 | 10/05/2024 | M/S MAA MANASA CONSTRUCTION CO. | 9.71 | 9.65 | 99.38 | 30
2 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 18/CD | 05/01/2024 | 05/01/2024 | Resource Division | 19.1 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Electric quotation bill for Phalimari Z-II, PH-II |  |  | BILL/01582/2024-2025 | BP-414/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 20.6 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | NEW SERVICE CONNECTION AT PHALIMARI PWSS ZONE-I, PH-I |  |  | BILL/00887/2024-2025 | BP-284/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 7.59 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | NEW SERVICE CONNECTION AT PHALIMARI PWSS ZONE-I, PH-II |  |  | BILL/00886/2024-2025 | BP-285/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 7.14 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Electric quotation for Phalimari Z-II, P-I |  |  | BILL/01583/2024-2025 | BP-413/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 13.28 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Execution of different works related to PHALIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000099/2023-2024 | 713/CD | 25/07/2023 | 11/08/2025 | TAPAN CHANDA | 871.31 | 324.71 | 37.27 | 40
8 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for PHALIMARI Water Supply Scheme TW No.I and II of Zone-I and TW No.I and II of Zone-II under NMD-II,PHE.Dte,APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000918/2023-2024 | 2492/NMD-II | 14/08/2023 | 29/04/2025 | CHOWDHURY AND BASU ENTERPRISE | 41.1 | 0 | 0 | 90
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 284.76 | 1.44 | 20
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PHALIMARI PIPED WATER SUPPLY SCHEME. | SM/18371 | New | Execution of different works related (Within area of DEWANHAT) to PHALIMARI & adjacent of MOAMARI & BRAHMOTTAR KASAL DANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000067/2024-2025 | 1324/CD | 19/07/2024 | 20/07/2025 | DAS ENTERPRISE | 45.49 | 15.01 | 32.99 | 30
Total | [13 empty] | 20824.62 | 634.12 | 3.05