## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai Water Supply Scheme under Cooch Behar Division, PHED. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000386/2023-2024 | 1089/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
2 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000387/2023-2024 | 1090/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000385/2023-2024 | 1088/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000384/2023-2024 | 1087/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000383/2023-2024 | 1086/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 179/CD | 27/04/2023 | 27/04/2023 | Resource Division | 33 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Execution of different works related to BHOGRAMGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000554/2023-2024 | 636/CD | 11/03/2024 | 10/05/2024 | SSPR VALVE MANUFACTURING PVT. LTD. | 91.19 | 53.61 | 58.79 | 70
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Execution of different works related to JAMALDAH HAT (Bhogramguri Adj. Area) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000028/2023-2024 | 382/CD | 23/05/2023 | 22/07/2023 | NORTH BENGAL CONSTRUCTION CO | 14.78 | 9.81 | 66.36 | 61
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Wall Painting, Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part D | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000517/2023-2024 | 315/CD | 09/02/2024 | 09/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 64.95 | 64.88 | 99.89 | 69
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 22/CD | 05/01/2024 | 05/01/2024 | Resource Division | 23.16 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHOGRAMGURI TW II. |  |  | BILL/00337/2024-2025 | BP-110/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BHOGRAMGURI TW I. |  |  | BILL/00336/2024-2025 | BP-109/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 6.76 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | LT PLE SHTING AND ALLIED WORKS |  |  | BILL/00376/2024-2025 | BP-320 | 31/08/2024 | 31/08/2024 | WBSEDCL | 0.22 | 0 | 0 | 0
14 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Execution of different works related to BHOGRAMGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000106/2023-2024 | 720/CD | 25/07/2023 | 16/03/2025 | Z STAR COMMOTRADE PVT LTD | 998.17 | 613.62 | 61.48 | 38
15 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bhogramguri Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001148/2023-2024 | 2902/NMD-II | 19/10/2023 | 06/01/2026 | DEY ENTERPRISE (BALLY) | 22.39 | 0 | 0 | 50
16 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 639.85 | 3.23 | 20
17 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000090/2025-2026 | 758/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 32.02 | 0 | 0 | 0
18 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BHOGRAMGURI & ITS ADJOINING MOUZAS PWSS | SM/18411 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000276/2025-2026 | 738/CD | 17/05/2025 | 15/08/2025 | SUBHAS CHANDRA ROY | 47.78 | 0 | 0 | 0
Total | [13 empty] | 21132.42 | 1386.69 | 6.56