## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Execution of different works related to DAKSHIN BOKA BANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000105/2023-2024 | 719/CD | 25/07/2023 | 16/03/2025 | MS BIDYUT SARKAR | 757.33 | 526.74 | 69.55 | 42
2 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 88/CD | 11/01/2024 | 11/01/2024 | Resource Division | 16.87 | 0 | 0 | 0
3 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DAKSHIN BOKNABANDHA TW I |  |  | BILL/00628/2024-2025 | BP-159/24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
4 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakshin Bokna Bandha Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000902/2023-2024 | 2472/NMD-II | 11/08/2023 | 21/06/2025 | M/S P.P ELECTRICALS | 21.78 | 0 | 0 | 50
5 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | EXECUTION OF DIFFERENT WORKS RELATED TO Dakshin Boknabandha PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000535/2024-2025 | 2219/CD | 23/12/2024 | 21/02/2025 | MS BIDYUT SARKAR | 57.05 | 29.84 | 52.31 | 30
7 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Execution of different works related to D BOKNA BANDNA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000043/2024-2025 | 1151/CD | 14/06/2024 | 11/03/2025 | MS BIDYUT SARKAR | 97.06 | 79.89 | 82.31 | 30
8 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000049/2025-2026 | 724/CD | 17/05/2025 | 15/08/2025 | AASHIRBAD ENTERPRISE | 83.45 | 0 | 0 | 0
9 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Extension of work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I, DAKSHIN BOKNA BANDHA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000709/2024-2025 | 416/CD | 19/03/2025 | 19/09/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
10 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Extension of work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I, DAKSHIN BOKNA BANDHA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000713/2024-2025 | 420/CD | 19/03/2025 | 19/09/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
11 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Extension of work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II, DAKSHIN BOKNA BANDHA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000712/2024-2025 | 419/CD | 19/03/2025 | 19/09/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
12 | COOCHBEHAR | Mekliganj | Coochbehar Division | DAKSHIN BOKNA BANDHA PIPED WATER SUPPLY SCHEME | SM/18412 | New | Extension of work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II, DAKSHIN BOKNA BANDHA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000710/2024-2025 | 417/CD | 19/03/2025 | 19/09/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
Total | [13 empty] | 20832.25 | 636.47 | 3.06