## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Execution of different works related to FALIMARI (ZONE-I) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000138/2023-2024 | 807/CD | 08/08/2023 | 05/01/2024 | HARIDAS GHOSH | 325.52 | 186.78 | 57.38 | 80
2 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Execution of different works related to FALIMARI ZONE I PWSS under JAL JEEVAN MISSION |  |  | ORD/000487/2023-2024 | 289/CD | 09/02/2024 | 09/04/2024 | GOUTAM KUMAR DAS | 96.73 | 79.07 | 81.75 | 81
3 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 96/CD | 11/01/2024 | 11/01/2024 | Resource Division | 17.58 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | QUOTATION FOR NSC AT FALIMARI TW NO I,Z-I |  |  | BILL/02469/2023-2024 | BP-2023-24-534 | 17/01/2024 | 17/01/2024 | WBSEDCL | 4.95 | 0 | 0 | 0
5 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | EXECUTION OF DIFFRENT WORKS AT PUTIMARI BAKSIBAS PWSS |  |  | BILL/01397/2023-2024 | BP-789 | 08/12/2023 | 08/12/2023 | NABIN DEBNATH | 30.77 | 0 | 0 | 0
6 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | QUOTATION FOR NSC AT FALIMARI TW NO II,Z-I |  |  | BILL/02466/2023-2024 | BP-2023-24-535 | 17/01/2024 | 17/01/2024 | WBSEDCL | 2.99 | 0 | 0 | 0
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
8 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | DAKSHIN BAJEJAMA KHASBAS PWSS |  |  | BILL/01322/2023-2024 | BP-782-P2 | 08/12/2023 | 08/12/2023 | ASOK KUMAR DHAR | 0.04 | 0 | 0 | 0
9 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Charges for new service connection at Falimari(Zone-II) PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/01883/2024-2025 | BP-422/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 4.06 | 0 | 0 | 0
10 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Execution of different works related to FALIMARI (ZONE-II) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000139/2023-2024 | 808/CD | 08/08/2023 | 30/03/2025 | AKBAR ALI | 404.81 | 254.43 | 62.85 | 76
11 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 284.53 | 1.44 | 20
12 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (NAGAR CHANGRABANDAAND MEGH NARAYANER KUTHI ) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000509/2024-2025 | 1794/CD | 30/09/2024 | 10/10/2024 | BIJOY ROY | 67.98 | 0 | 0 | 95
13 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TATERKUTHI KHAGRIBARI GORBHANGA & FALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000557/2024-2025 | 2242/CD | 23/12/2024 | 21/02/2025 | HARIDAS GHOSH | 65.94 | 14.35 | 21.76 | 60
14 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
15 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | FALIMARI PIPED WATER SUPPLY SCHEME | SM/18616 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000098/2025-2026 | 751/CD | 17/05/2025 | 15/08/2025 | TAPAN CHANDA | 18.09 | 0 | 0 | 0
Total | [13 empty] | 21364.37 | 819.16 | 3.83