## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 171/CD | 27/04/2023 | 27/04/2023 | Resource Division | 79.84 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | QUOTATION FOR NSC AT BHORM PH NO-I |  |  | BILL/01744/2023-2024 | BP-2023-24-341 | 27/09/2023 | 27/09/2023 | WBSEDCL | 8.34 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | QUOTATION FOR NSC AT BHORM PH NO-III |  |  | BILL/01747/2023-2024 | BP-2023-24-343 | 27/09/2023 | 27/09/2023 | WBSEDCL | 9.91 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | QUOTATION FOR NSC AT BHORM PH NO-II |  |  | BILL/01745/2023-2024 | BP-2023-24-342 | 27/09/2023 | 27/09/2023 | WBSEDCL | 8.06 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Laying DI P/Line & other allied works related to BHORAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000598/2023-2024 | 641/CD | 11/03/2024 | 10/05/2024 | MS BIDYUT SARKAR | 92.45 | 67.47 | 72.98 | 25
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Laying DI P/Line & other allied works related to BHORAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000571/2023-2024 | 613/CD | 11/03/2024 | 10/05/2024 | MS BIDYUT SARKAR | 78.23 | 66.57 | 85.09 | 30
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BHORAM PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000515/2024-2025 | 2283/CD | 23/12/2024 | 21/02/2025 | MS BIDYUT SARKAR | 34.22 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part G | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000584/2023-2024 | 600/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 54.64 | 13.85 | 25.34 | 100
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 29/CD | 05/01/2024 | 05/01/2024 | Resource Division | 20.57 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Execution of different works related to BHORAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000146/2023-2024 | 860/CD | 22/08/2023 | 19/03/2025 | MS BIDYUT SARKAR | 728.84 | 601.14 | 82.48 | 66
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (NAGAR CHANGRABANDAAND MEGH NARAYANER KUTHI ) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000509/2024-2025 | 1794/CD | 30/09/2024 | 10/10/2024 | BIJOY ROY | 67.98 | 0 | 0 | 95
13 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
14 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHORAM PIPED WATER SUPPLY SCHEME | SM/18720 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhoram water supply scheme, TW no I,II and III of under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000834/2023-2024 | 2416/NMD-II | 10/08/2023 | 09/09/2023 | NUPUR CHANDRA HALDER | 33.95 | 18.5 | 54.48 | 100
Total | [13 empty] | 21494.4 | 767.52 | 3.57