## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 156/CD | 27/04/2023 | 27/04/2023 | Resource Division | 29.97 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 78/CD | 11/01/2024 | 11/01/2024 | Resource Division | 16.41 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Charges for new service connection at Garbhadanga pwss, P/H-II |  |  | BILL/00207/2024-2025 | BP-45/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.67 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Charges for new service connection at Garbhadanga PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01651/2024-2025 | BP-407/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 4.29 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Charges for new service connection at Garbhadanga pwss, P/H-I |  |  | BILL/00206/2024-2025 | BP-44/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 5.14 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Execution of different works related to GARBHADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000144/2023-2024 | 862/CD | 22/08/2023 | 23/04/2025 | S & P ENTERPRISE | 519.67 | 0 | 0 | 70
7 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (NAGAR CHANGRABANDAAND MEGH NARAYANER KUTHI ) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000509/2024-2025 | 1794/CD | 30/09/2024 | 10/10/2024 | BIJOY ROY | 67.98 | 0 | 0 | 95
9 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000054/2025-2026 | 602/CD | 28/04/2025 | 27/07/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Garbhadanga Piped Water Supply Scheme. | SM/18749 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GARBHADANGA water supply scheme, TW no-I ,II and III under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/002037/2023-2024 | 1186/NMD-II | 11/03/2024 | 03/03/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 31.66 | 0 | 0 | 100
Total | [13 empty] | 20565.9 | 0 | 0