## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Execution of different works related to SAJHERPAR GHORAMARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000143/2023-2024 | 863/CD | 02/08/2023 | 30/12/2023 | Z STAR COMMOTRADE PVT LTD | 742.64 | 509.9 | 68.66 | 55
2 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sajerpar Ghoramara TG water supply scheme, TW no I and II of Zone-I and TW no I of Zone-II under NMD-II, PHE Dte.APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001126/2023-2024 | 2870/NMD-II | 17/10/2023 | 16/11/2023 | WEST BENGAL ENGINEERING CO. | 35.36 | 29.6 | 83.72 | 70
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Name of Work: Execution of different works related to KALARAYERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000258/2023-2024 | 1023/CD | 22/09/2023 | 01/04/2025 | SANKAR BANIK | 90.78 | 82.91 | 91.33 | 62
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 128/CD | 27/04/2023 | 27/04/2023 | Resource Division | 11.83 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000525/2024-2025 | 2288/CD | 23/12/2024 | 21/06/2025 | M/S MAA MANASA CONSTRUCTION CO. | 34.93 | 0 | 0 | 60
7 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Execution of different works related to SAJERPAR GHORAMARA PWSS under JAL JEEVAN MISSION | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000567/2023-2024 | 609/CD | 11/03/2024 | 21/07/2025 | AKANSHA COMMERCIAL PVT. LTD. | 94.4 | 0 | 0 | 30
8 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai, SAJHERPAR GHORAMARA Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000493/2024-2025 | 1084/CD | 29/05/2024 | 29/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II, SAJHERPAR GHORAMARA Piped Water Supply Scheme under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000492/2024-2025 | 1083/CD | 28/05/2024 | 28/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
10 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi, SAJHERPAR GHORAMARA Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000494/2024-2025 | 1085/CD | 30/05/2024 | 30/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
11 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I, SAJHERPAR GHORAMARA Piped Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000490/2024-2025 | 1082/CD | 27/05/2024 | 27/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
12 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 26/CD | 05/01/2024 | 05/01/2024 | Resource Division | 18.71 | 0 | 0 | 0
13 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR GHORAMARA PWSS PH-III |  |  | BILL/00169/2024-2025 | BP-40/24-25 | 26/04/2024 | 26/04/2024 | WBSEDCL | 6.57 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR GHORAMARA PH-IV |  |  | BILL/00170/2024-2025 | BP-39/24-25 | 26/04/2024 | 26/04/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
15 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR GHORAMARA PH-II |  |  | BILL/02874/2023-2024 | BP-2023-24-650 | 04/03/2024 | 04/03/2024 | WBSEDCL | 5.65 | 0 | 0 | 0
16 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR GHORAMARA PWSS PH-III |  |  | BILL/00168/2024-2025 |  | 23/04/2024 | 23/04/2024 | WBSEDCL | 6.57 | 0 | 0 | 0
17 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | NEW SERVICE CONNECTION CHARGES AT SAJERPAR GHORAMARA PWSS, PH - I |  |  | BILL/02733/2023-2024 | BP-2023-24-609 | 16/02/2024 | 16/02/2024 | WBSEDCL | 5.69 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Sajerpar Ghoramara PWSS,TW No.- III OF Zone-I under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/000090/2025-2026 | 1232/NMD-II | 29/05/2025 | 28/06/2025 | DIPA CHHETRI | 11.26 | 0 | 0 | 0
20 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | Solarization of grid connected pumping installation at Different PWSS at Coochbehar-II Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000136/2025-2026 | 1336/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
21 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000082/2025-2026 | 691/CD | 15/05/2025 | 08/08/2026 | MATARA CONSTRUCTION CO. | 31.28 | 0 | 0 | 0
22 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR GHORAMARA PIPED WATER SUPPLY SCHEME | SM/18751 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000256/2025-2026 | 754/CD | 17/05/2025 | 15/08/2025 | M/S T M CONSTRUCTION | 95.38 | 0 | 0 | 0
Total | [13 empty] | 21497.79 | 626.35 | 2.91