## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 254/CD | 27/04/2023 | 27/04/2023 | Resource Division | 39.47 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Laying of Pipe line Construction of Pump House & B/Wall at 3rd Site of SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000148/2023-2024 | 858/CD | 21/08/2023 | 18/01/2024 | MS SSB CONSTRUCTION CO | 121.49 | 66.25 | 54.53 | 61
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Sinking of Big Dia Tubewell at HWSite & 2nd Site of SHIKARPUR PWSS under JAL JEEVAN MISSION (Z-I : 3rd Site Z-II : HW & 2nd Site | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000155/2023-2024 | 853/CD | 21/08/2023 | 19/11/2023 | MATARA CONSTRUCTION CO. | 35.05 | 32.01 | 91.34 | 92
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Execution of different works related to SIKARPUR PWSS under JAL JEEVAN MISSION MKG | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000488/2023-2024 | 290/CD | 09/02/2024 | 09/04/2024 | M/S SURAJIT MAJUMDER | 5.06 | 5.03 | 99.4 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | LAND REGISTRATION |  |  | BILL/00591/2024-2025 | BP-226 | 01/08/2024 | 01/08/2024 | SWAPAN KR.SARKAR | 0.88 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | LAND REGISTRATION |  |  | BILL/00594/2024-2025 | BP-229 | 01/08/2024 | 01/08/2024 | SWAPAN KR.SARKAR | 0.87 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | LAND REGIGRATION |  |  | BILL/00593/2024-2025 | BP-227 | 01/08/2024 | 01/08/2024 | SWAPAN KR.SARKAR | 0.86 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | RAGISTRATION OF LAND |  |  | BILL/00592/2024-2025 | BP-228 | 01/08/2024 | 01/08/2024 | SWAPAN KR.SARKAR | 0.84 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | EXECUTION FO DIFFERENT WORKS AT RAMPUR PWSS |  |  | BILL/00590/2024-2025 | BP-225 | 01/08/2024 | 01/08/2024 | GOUTAM KUMAR DAS | 4.16 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Execution of different works related to AUG. of Shikarpur Zone-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000154/2023-2024 | 854/CD | 21/08/2023 | 18/01/2024 | AMBITIOUS ENTERPRISE | 450.34 | 77.48 | 17.2 | 18
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Construction of 450 cum OHR and Laying of Pipe line at SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000151/2023-2024 | 855/CD | 21/08/2023 | 09/09/2025 | GHOSH AND SAHA CONSTRUCTION | 276.33 | 120.26 | 43.52 | 60
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Providing FHTC and Laying of Pipe line of SHIKARPUR ZONE ? II PWSS under JAL JEEVAN MISSION (PART ?D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000156/2023-2024 | 865/CD | 22/08/2023 | 13/05/2025 | M/S NARAYAN KR. GHOSH | 83.42 | 73.05 | 87.58 | 65
13 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF SIKARPUR Water Supply Scheme TW No.- I of Zone-I and I and II of Zone-II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001091/2023-2024 | 2810/NMD-II | 09/10/2023 | 01/09/2025 | M/S SAJAHAN CHOWDHURY | 31.75 | 26.45 | 83.31 | 40
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 639.85 | 3.23 | 20
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000123/2025-2026 | 763/CD | 17/05/2025 | 15/08/2025 | AKANSHA COMMERCIAL PVT. LTD. | 68.77 | 0 | 0 | 30
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000254/2025-2026 | 761/CD | 17/05/2025 | 15/08/2025 | AKANSHA COMMERCIAL PVT. LTD. | 67.3 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000276/2025-2026 | 738/CD | 17/05/2025 | 15/08/2025 | SUBHAS CHANDRA ROY | 47.78 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Providing FHTC & Laying of Pipe line of SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000150/2023-2024 | 856/CD | 21/08/2023 | 19/02/2025 | MATARA CONSTRUCTION CO. | 109.25 | 101.09 | 92.53 | 100
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | SM/18757 | Augmentation | Providing FHTC & Laying of Pipe line of SHIKARPUR ZONE ? I PWSS under JAL JEEVAN MISSION (PART ?D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000149/2023-2024 | 857/CD | 21/08/2023 | 11/02/2025 | M/S. NITYAGOPAL BANIK | 145.55 | 27.7 | 19.03 | 95
Total | [13 empty] | 21278.44 | 1169.19 | 5.49