## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | Mansai Piped Water Supply Scheme. | SM/18764 | New | Execution of different works related to MANSAI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000159/2023-2024 | 881CD | 25/08/2023 | 16/04/2025 | GOUTAM KUMAR DAS | 325.95 | 283.9 | 87.1 | 78
2 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | Mansai Piped Water Supply Scheme. | SM/18764 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANSAI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001139/2023-2024 | 2874/NMD-II | 17/10/2023 | 16/11/2023 | SANJIB SAHA | 21.02 | 9.88 | 47 | 40
3 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | Mansai Piped Water Supply Scheme. | SM/18764 | New | Execution of different works related to MANSAI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000429/2023-2024 | 1485/CD | 20/12/2023 | 18/02/2024 | GOUTAM KUMAR DAS | 96.93 | 80.26 | 82.81 | 82
4 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | Mansai Piped Water Supply Scheme. | SM/18764 | New | QUOTATION FOR NSC AT MANSAI TW NO-I |  |  | BILL/01847/2023-2024 | BP-2023-24-388 | 06/10/2023 | 06/10/2023 | WBSEDCL | 2.96 | 0 | 0 | 0
5 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | Mansai Piped Water Supply Scheme. | SM/18764 | New | QUOTATION FOR NSC AT MANSAI TW NO-II |  |  | BILL/01846/2023-2024 | BP-2023-24-387 | 06/10/2023 | 06/10/2023 | WBSEDCL | 3.3 | 0 | 0 | 0
6 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | Mansai Piped Water Supply Scheme. | SM/18764 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 90.4 | 0.46 | 20
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | Mansai Piped Water Supply Scheme. | SM/18764 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SIGN BOARD AT EVERY LANDS OF DIFFERENT PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000623/2024-2025 | 2325/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 44.29 | 0 | 0 | 100
8 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | Mansai Piped Water Supply Scheme. | SM/18764 | New | Installation & Trial operation of departmentally supplied pumping machinery & other electro-mechanical components at P/H-II under Mansai w/s scheme in the dist of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000035/2024-2025 | 1923/CMSD | 10/06/2024 | 25/06/2024 | M/S SAJAHAN CHOWDHURY | 1.09 | 0 | 0 | 100
9 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | Mansai Piped Water Supply Scheme. | SM/18764 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000080/2025-2026 | 784/CD | 23/05/2025 | 21/08/2025 | GOUTAM KUMAR DAS | 92.33 | 0 | 0 | 0
Total | [13 empty] | 20377.16 | 464.44 | 2.28