## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Kuchni Pratham Khanda Piped Water Supply Scheme. | SM/18781 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 157/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.21 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Kuchni Pratham Khanda Piped Water Supply Scheme. | SM/18781 | New | Execution of different works related to KUCHNI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000162/2023-2024 | 893/CD | 31/08/2023 | 28/01/2024 | M/S TORSHA CONSTRUCTION | 342.08 | 231.28 | 67.61 | 48
3 | COOCHBEHAR | Dinhata-II | Coochbehar Division | Kuchni Pratham Khanda Piped Water Supply Scheme. | SM/18781 | New | Laying DI P/Line & other allied works related to KUCHNI P KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000575/2023-2024 | 596/CD | 11/03/2024 | 10/05/2024 | TORSHA CONSTRUCTION | 83.65 | 54.42 | 65.06 | 40
4 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Kuchni Pratham Khanda Piped Water Supply Scheme. | SM/18781 | New | Charges for new service connection at Kuchni pratham khanda PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/00821/2024-2025 | BP-242/24-25 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.21 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Kuchni Pratham Khanda Piped Water Supply Scheme. | SM/18781 | New | Charge for New service connection at Kuchni pratham khanda PWSS, P/H-I in the dist of Coochbehar. |  |  | BILL/00822/2024-2025 | BP-243/24-25 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.11 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | Kuchni Pratham Khanda Piped Water Supply Scheme. | SM/18781 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KUCHNI PRATHAM KHANDA water supply scheme, TW no-I and II Under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/002042/2023-2024 | 1190/NMD-II | 11/03/2024 | 10/04/2024 | HARAGOURI ENTERPRISE | 21.87 | 15.93 | 72.85 | 80
Total | [13 empty] | 470.13 | 301.64 | 64.16