## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation Of Kholta Water Supply Scheme TWNo- I,of Zone-I and T/W No.I &II of Zone-II under NMD-II,PHE.Dte,APD. |  |  | ORD/001073/2023-2024 | 2736/NMD-II | 26/09/2023 | 26/10/2023 | P K ENGINEERING | 32.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 251/CD | 27/04/2023 | 27/04/2023 | Resource Division | 32.1 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Execution of different works related to KHOLTA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000161/2023-2024 | 892/CD | 31/08/2023 | 28/01/2024 | M/S T R PARIK | 723.82 | 491.64 | 67.92 | 55
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Execution of different works related (Within area of BANESWAR ZIII) to KHOLTA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000350/2023-2024 | 1334/CD | 24/11/2023 | 23/01/2024 | ASHIT KUMAR GHOSH | 29.89 | 28.04 | 93.81 | 95
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Execution of different works related to KHOLTA PWSS under JAL JEEVAN MISSION P B | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION |  | ORD/000062/2024-2025 | 1714/CD | 25/09/2024 | 24/12/2024 | M/S T R PARIK | 88.08 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | NEW SERVICE CONNECTION AT KHOLTA PWSS ZONE-II PH-I |  |  | BILL/02013/2024-2025 | BP-421/24-25 | 14/12/2024 | 14/12/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at KHOLTA adjacent KUMIRGHAT W.S.S under Cooch Behar Division P.H.E.Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000537/2021-2022 | 1637/CD | 29/03/2022 | 24/06/2025 | ANIMESH DHAR CHOUDHURY | 33.41 | 0 | 0 | 52
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | Execution of different works within KHOLTA area related to AUG. GOPALPUR PWSS under JAL JEEVAN MISSION P A | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000032/2024-2025 | 1141/CD | 14/06/2024 | 10/04/2025 | DIPANKAR BANIK | 51.38 | 0 | 0 | 50
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000036/2025-2026 | 721/CD | 17/05/2025 | 15/08/2025 | BIJOY ROY | 16.73 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | SM/18788 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000275/2025-2026 | 739/CD | 17/05/2025 | 15/08/2025 | DAS ENTERPRISE | 37.76 | 0 | 0 | 0
Total | [13 empty] | 1049.92 | 519.67 | 49.5