## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | Solarisation of WBSEDCL Energised Electrical Installation at Bogdabari Kesaibari PWSS and Others in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. | SM/16634 |  | Solarization of grid connected pumping installation at different PWSS in the Dist of CoochBehar under JJM programe under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000486/2023-2024 | 1761/NMD-II | 18/07/2023 | 15/11/2023 | MEGA SOLAR ENERGY | 93.43 | 0 | 0 | 60
2 | COOCHBEHAR |  | Northern Mechanical Division II | Solarisation of WBSEDCL Energised Electrical Installation at Bogdabari Kesaibari PWSS and Others in CoochBehar District under Northern Mechanical Division-II, P.H.E. Dte. | SM/16634 |  | Charges for replacement of meter for Net Metering at Bhogdabari kesaibari PWSS in the dist of Coochbehar. |  |  | BILL/00988/2024-2025 | null | 14/08/2024 |  | WBSEDCL | 0.18 | 0 | 0 | null
Total | [13 empty] | 93.61 | 0 | 0