## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | Implementation of Affordable IOT System at Rampur (Zone-I) Water Supply Scheme in Tufanganj-II Block of Coochbehar district under Northern Mechanical Division-II, P.H.E. Dte. | SM/17951 | IOT | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Different Block of Alipurduar and Coochbehar District in West Bengal | Assistant Engineer, Cooch-Behar Mechanical Sub-Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001199/2024-2025 | 807/NMD-II | 04/03/2025 | 31/08/2025 | WEBEL TECHNOLOGY LIMITED | 594.37 | 0 | 0 | 0
Total | [13 empty] | 594.37 | 0 | 0