## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs | SM/06641 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Itahar Sub-District Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000063/2021-2022 | 1786/RD/PHE | 10/09/2021 | 25/09/2021 | DULAL MAJUMDER | 4.97 | 4.97 | 100 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs | SM/06641 | Support-WQMSP | LABORATORY BILL | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000762/2021-2022 | 1162/RD | 01/06/2021 | 28/11/2021 | DULAL MAJUMDER | 4.16 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs | SM/06641 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Raiganj District Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000059/2021-2022 | 1782/RD/PHE | 10/09/2021 | 25/09/2021 | DULAL MAJUMDER | 5 | 4.86 | 97.2 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs | SM/06641 | Support-WQMSP | SUPPLY OF CHEMICAL & GLASSWARE FOR LABORATORY UNDER RAIGANJ DIVISION PHED |  |  | ORD/000502/2018-2019 | 1432/RD | 28/11/2018 |  | DULAL MAJUMDER | 25.25 | 8 | 31.67 | 0
Total | [13 empty] | 39.37 | 17.82 | 45.27