## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | FHTC OF BIPRIT PWSS | Assistant Engineer ISD |  | ORD/000368/2020-2021 | 1497/RD | 23/12/2020 | 17/01/2021 | HERO CONSTRUCTION | 3.52 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002099/2021-2022 | 768/W | 11/03/2022 | 11/03/2022 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Biprit and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000180/2020-2021 | 1244/RD/PHE | 16/10/2020 | 25/11/2020 | PRASANTO DUTTA | 90.07 | 0 | 0 | 0
Total | [13 empty] | 93.68 | 0 | 0