## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | FHTC OF BIPRIT PWSS | Assistant Engineer ISD |  | ORD/000368/2020-2021 | 1497/RD | 23/12/2020 | 17/01/2021 | HERO CONSTRUCTION | 3.52 | 3.84 | 109.17 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002099/2021-2022 | 768/W | 11/03/2022 | 11/03/2022 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Biprit and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000180/2020-2021 | 1244/RD/PHE | 16/10/2020 | 25/11/2020 | PRASANTO DUTTA | 90.07 | 4.49 | 4.98 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0.19 | 7.17 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 15.01.2025 to 14.07.2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000808/2024-2025 | 298/RD/PHE | 15/01/2025 | 15/07/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.4 | 1.98 | 82.29 | 60
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme | SM/06722 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 30.12.2024 & 31.12.2024. |  |  | BILL/00937/2024-2025 | 844364 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
Total | [13 empty] | 98.71 | 10.49 | 10.62