## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Nalbithi Madhabpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000178/2020-2021 | 1238/RD/PHE | 16/10/2020 | 25/11/2020 | M/S LOKENATH CONST | 91.32 | 2.07 | 2.27 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.07.2024 upto 14.01.2025). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000053/2024-2025 | 2159/RD/PHE | 15/07/2024 | 15/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 1.37 | 57.21 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 29/12/2024 | DEBASISH GHOSH | 2.6 | 0.14 | 5.4 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000807/2024-2025 | 296/RD/PHE | 15/01/2025 | 15/07/2025 | DEBASISH GHOSH | 2.4 | 0.66 | 27.31 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 26.12.2024 & 27.12.2024. |  |  | BILL/00939/2024-2025 | 8443108 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 27.1.2025 & 29.01.2025. |  |  | BILL/00958/2024-2025 | 8443115 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme | SM/06723 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 01.10.2024 & 03.10.2024. |  |  | BILL/00940/2024-2025 | 8443112 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.02 | 0 | 0 | 0
Total | [13 empty] | 98.79 | 4.24 | 4.29