## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme | SM/06724 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Sripur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000123/2020-2021 | 1237/RD/PHE | 16/10/2020 | 25/11/2020 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 80.5 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme | SM/06724 | Retrofitting | LAYING FITTING FHTC OF SRIPUR WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000156/2020-2021 | 1523/RD | 23/12/2020 | 22/01/2021 | MS SARKAR ENTERPRISE ABDULGHATA | 8.14 | 11.25 | 138.23 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme | SM/06724 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.07.2024 upto 14.01.2025). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000053/2024-2025 | 2159/RD/PHE | 15/07/2024 | 15/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0.77 | 32.17 | 0
Total | [13 empty] | 91.04 | 12.03 | 13.21