## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme | SM/06725 | Retrofitting | Supply, laying, fitting, fixing & jointing of upvc pipe including PCC & ordinary concrete( 1:2:4) connection with retrofitting of functional household tap connection (FHTC) under MAHAMMADPUR water Supply Scheme Under Raiganj Division, P.H.E.Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000467/2020-2021 | 1501/RD/PHE | 23/12/2020 | 17/01/2021 | ANILA CONSTRUCTION | 3.11 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme | SM/06725 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002090/2021-2022 | 773/W | 11/03/2022 | 11/03/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme | SM/06725 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Mahammadpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000181/2020-2021 | 1239/RD/PHE | 16/10/2020 | 25/11/2020 | TAPAN KUMAR DUTTA | 84.41 | 26.21 | 31.05 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme | SM/06725 | Retrofitting | FHTC OF MAHAMMADPUR WSS | Assistant Engineer RSD |  | ORD/000012/2020-2021 | 1239/RD | 16/10/2020 | 25/11/2020 | TAPAN KUMAR DUTTA | 84.41 | 106.32 | 125.96 | 0
Total | [13 empty] | 172.01 | 132.53 | 77.04