## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme | SM/06726 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Barabilla and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000179/2020-2021 | 1241/RD/PHE | 16/10/2020 | 25/11/2020 | BHOLA PAUL | 62.49 | 52.93 | 84.7 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme | SM/06726 | Retrofitting | FHTC OF BARABILLA PWSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000451/2020-2021 | 1505/RD/PHE | 23/12/2020 | 22/01/2021 | M/S LUCKY CONSTRUCTION | 11.66 | 11.65 | 99.85 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme | SM/06726 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002104/2021-2022 | 767/W | 11/03/2022 | 11/03/2022 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme | SM/06726 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002096/2021-2022 | 771/W | 11/03/2022 | 11/03/2022 | M/S DUTTA ENTERPRISE | 0.07 | 0 | 0 | 0
Total | [13 empty] | 74.32 | 64.58 | 86.89