## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002105/2021-2022 | 766/W | 11/03/2022 | 11/03/2022 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | HIRE CHRAGE OF VEHICLE |  |  | VCH/001273/2022-2023 | 322/W | 14/09/2022 | 14/09/2022 | JOYDEB GHOSH | 0.06 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Chhotaparua and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000206/2020-2021 | 1243/RD/PHE | 16/10/2020 | 25/11/2020 | PRASANTA DUTTA | 77.11 | 12.04 | 15.62 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Chotaparua Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000282/2022-2023 | 496/RD/PHE | 17/02/2023 | 03/04/2023 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 3.18 | 2.91 | 91.36 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 10/01/2025 | MD ZAFAR EQUEBAL | 2.6 | 2.28 | 87.87 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 15.01.2025 to 14.07.2025.) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000812/2024-2025 | 301/RD/PHE | 15/01/2025 | 15/07/2025 | MD ZAFAR EQUEBAL | 2.4 | 2.16 | 89.91 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000807/2024-2025 | 296/RD/PHE | 15/01/2025 | 15/07/2025 | DEBASISH GHOSH | 2.4 | 0.79 | 33.01 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 12.11.2024 & 14.11.2024. |  |  | BILL/00943/2024-2025 | 8443111 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 22.10.2024 & 24.10.2024. |  |  | BILL/00945/2024-2025 | 8443107 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme | SM/06727 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 22.11.2024 & 25.11.2024. |  |  | BILL/00944/2024-2025 | 8443110 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
Total | [13 empty] | 87.92 | 20.18 | 22.95