## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | FHTC OF DEBIGANJ WSS |  |  | ORD/000111/2020-2021 | 1512/RD | 23/12/2020 | 22/01/2021 | HAQUE CONSTRUCTION | 18.37 | 36.68 | 199.62 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Debiganj and adjoining Mouzas water supply scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000207/2020-2021 | 1236/RD/PHE | 16/10/2020 | 25/11/2020 | HAQUE CONSTRUCTION | 56.27 | 0.32 | 0.58 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | FHTC FOR DEBIGANJ WSS | Assistant Engineer ISD |  | ORD/000016/2020-2021 | 1236/RD | 16/10/2020 | 25/11/2020 | HAQUE CONSTRUCTION | 56.27 | 107.3 | 190.69 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59C 0644) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 15/01/2025 to 14/07/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000864/2024-2025 | 302/RD/PHE | 15/01/2025 | 15/07/2025 | PRITAM SARKAR | 2.4 | 0.4 | 16.64 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (Period for 15/01/2025 to 14/07/2025) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000811/2024-2025 | 300/RD/PHE | 15/01/2025 | 15/07/2025 | SISIR KUMAR DUTTA | 2.4 | 1.65 | 68.93 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 09.09.2024 & 13.09.2024. |  |  | BILL/00946/2024-2025 | 8443114 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 23.09.2024 & 26.09.2024 |  |  | BILL/00947/2024-2025 | 8443106 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 27.11.2024 & 28.11.2024. |  |  | BILL/00948/2024-2025 | 8443109 | 27/03/2026 | 27/03/2026 | SAHA CONSTRUCTION | 0.03 | 0 | 0 | 0
Total | [13 empty] | 135.79 | 146.35 | 107.78