## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | FHTC OF DEBIGANJ WSS |  |  | ORD/000111/2020-2021 | 1512/RD | 23/12/2020 | 22/01/2021 | HAQUE CONSTRUCTION | 18.37 | 18.34 | 99.81 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Debiganj and adjoining Mouzas water supply scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000207/2020-2021 | 1236/RD/PHE | 16/10/2020 | 25/11/2020 | HAQUE CONSTRUCTION | 56.27 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem | SM/06728 | Retrofitting | FHTC FOR DEBIGANJ WSS | Assistant Engineer ISD |  | ORD/000016/2020-2021 | 1236/RD | 16/10/2020 | 25/11/2020 | HAQUE CONSTRUCTION | 56.27 | 53.65 | 95.34 | 0
Total | [13 empty] | 130.91 | 71.99 | 54.99