## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme | SM/06729 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Siripur and adjoining Mouzas Water Supply Scheme in Galpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000171/2020-2021 | 1234/RD/ PHE | 16/10/2020 | 25/11/2020 | SAMIRAN PODDAR | 65.04 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme | SM/06729 | Retrofitting | LAYING UPVC OF FHTC OF SIRIPUR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000442/2020-2021 | 1522/RD | 23/12/2020 | 22/01/2021 | M/S DOLPHIN CONSTRUCTION | 6.9 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme | SM/06729 | Retrofitting | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (Period for 15/01/2025 to 14/07/2025) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000811/2024-2025 | 300/RD/PHE | 15/01/2025 | 15/07/2025 | SISIR KUMAR DUTTA | 2.4 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme | SM/06729 | Retrofitting | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (Period for 15/07/2025 to 14/01/2026). | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000215/2025-2026 | 2068/RD/PHE | 14/07/2025 | 14/01/2026 | SISIR KUMAR DUTTA | 2.4 | 0 | 0 | 85
Total | [13 empty] | 76.74 | 0 | 0