## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme | SM/06730 | Retrofitting | SUPPLYING LAYING FIXING AND JOINTING UPVC PIPE FHTC OF CHOPRABARI PWSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000429/2020-2021 | 1511/RD | 23/12/2020 | 22/01/2021 | M/S CHOUDHURY CONSTRUCTION | 8.56 | 8.45 | 98.72 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme | SM/06730 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002082/2021-2022 | 776/W | 11/03/2022 | 11/03/2022 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme | SM/06730 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Choprabari and adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000125/2020-2021 | 1242/RD/PHE | 16/10/2020 | 25/11/2020 | AJIT PARMANIK | 74.35 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme | SM/06730 | Retrofitting | FHTC OF CHOPRABARI | Assistant Engineer ISD |  | ORD/000014/2020-2021 | 1242/RD | 16/10/2020 | 25/11/2020 | AJIT PARMANIK | 74.59 | 98.13 | 131.56 | 0
Total | [13 empty] | 157.58 | 106.57 | 67.63