## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme | SM/06731 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Lodhan and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000182/2020-2021 | 1240/RD/PHE | 16/10/2020 | 25/11/2020 | J.D.J. ENTERPRISE | 65.65 | 24.4 | 37.16 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme | SM/06731 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002086/2021-2022 | 775/W | 11/03/2022 | 11/03/2022 | SAHA CONSTRUCTION | 0.06 | 0 | 0 | 0
Total | [13 empty] | 65.71 | 24.4 | 37.13