## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block | SM/07071 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kamartor and Adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000270/2020-2021 | 1414/RD/PHE | 11/12/2020 | 20/01/2021 | J.D.J. ENTERPRISE | 88.73 | 56.7 | 63.9 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block | SM/07071 | Retrofitting | Barbed Fencing work at Kamartor Head Work Site of Kamartor Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000184/2022-2023 | 2254/RD/PHE | 22/12/2022 | 09/08/2024 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 1.49 | 1.48 | 99.36 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block | SM/07071 | Retrofitting | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 1.52 | 31.7 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block | SM/07071 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000523/2024-2025 | 95/RD/PHE | 08/01/2025 | 08/07/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 0.48 | 19.95 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block | SM/07071 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 19-03-2025 and 24-03-2025. |  |  | BILL/01392/2025-2026 | 8443118 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.09 | 0 | 0 | 0
Total | [13 empty] | 97.51 | 60.18 | 61.71