## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | OFFICE ACCESSORIES BILL |  |  | VCH/002102/2021-2022 | 765/W | 11/03/2022 | 11/03/2022 | BEEKAY.COM | 0.1 | 0 | 0 | 0
2 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | Retrofitting of Functional Household Tap Connections(FHTC) at Sergram Part Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000167/2020-2021 | 1432/RD/PHE | 11/12/2020 | 10/01/2021 | M/S P.S ENTERPRISE | 17.7 | 0 | 0 | 0
3 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | Retrofitting of Functional Household Tap Connections(FHTC) at Sergram Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000261/2020-2021 | 1434/RD/PHE | 11/12/2020 | 10/01/2021 | AJIT PARMANIK | 18.68 | 0 | 0 | 0
4 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | Retrofitting of Functional Household Tap Connections(FHTC) at Shursa Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000163/2020-2021 | 1433/RD/PHE | 11/12/2020 | 10/01/2021 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 19.38 | 0 | 0 | 0
5 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 28/06/2024 | DEBASISH GHOSH | 4.8 | 2.38 | 49.49 | 0
6 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000807/2024-2025 | 296/RD/PHE | 15/01/2025 | 15/07/2025 | DEBASISH GHOSH | 2.4 | 0 | 0 | 0
7 |  |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block |  |  | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.07.2025 to 14.01.2026). | Assistant Engineer RSD |  | ORD/000217/2025-2026 | 2070/RD/PHE | 14/07/2025 | 14/01/2026 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0 | 0
Total | [13 empty] | 65.47 | 2.38 | 3.63