## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Laguar Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000274/2020-2021 | 1418/RD/PHE | 11/12/2020 | 10/01/2021 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 10.53 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Habipur Mouza under Amalbari and Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000272/2020-2021 | 1420/RD/PHE | 11/12/2020 | 10/01/2021 | SANJIB BHATTACHARJEE | 10.54 | 0 | 0 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Sahasra Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000273/2020-2021 | 1419/RD/PHE | 11/12/2020 | 10/01/2021 | LOKENATH CO-OP LBOUR CONTRACT &CONSTRUCTION SOCIETY LTD. | 10.56 | 0 | 0 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002089/2021-2022 | 772/W | 11/03/2022 | 11/03/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Baldoria Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000292/2020-2021 | 1440/RD/PHE | 11/12/2020 | 10/01/2021 | DIPANKAR SARKAR | 10.56 | 0 | 0 | 1
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Amalbari Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000275/2020-2021 | 1417/RD/PHE | 11/12/2020 | 10/01/2021 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 10.56 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) at Ranipur Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000276/2020-2021 | 467/RD/PHE | 26/02/2021 | 28/03/2021 | M/S BHOWMIK ENTERPRISE | 10.53 | 0 | 0 | 0
Total | [13 empty] | 63.34 | 0 | 0